## Title
Project Number | Team# (as allotted) | Title | A Lightweight, Sidecar-Free Service-to-Service Authentication Framework for Microservices
|  | (Previous titles) | NA | (in case you changed the project)
Guide | TBD | Team | Praneesh R V | CB.EN.U4CYS22___
|  |  | Sanjai K C K | CB.EN.U4CYS22___
|  |  | Dinesh V Masuti | CB.EN.U4CYS22___
|  |  | Akash Varunn D | CB.EN.U4CYS22___
Stack | Framework | Go standard library (crypto/tls, crypto/x509, net/http); go-spiffe v2 for the SPIRE Workload API
| Programming Languages | Go 1.26
| Scripting Languages | None in this phase
Description | Internal service-to-service (East-West) traffic in a microservice cluster is unauthenticated by
default, so a single compromised container can move laterally and reach any other service. The
standard fix is a service mesh, which closes the gap but adds 50 to 150 MB of memory per pod and
roughly 166 percent P99 latency in the sidecar model, and still cannot tell which end user
authorised a multi-hop request. This project builds an importable Go middleware library that
provides SPIFFE/SPIRE workload identity, in-process mutual TLS, embedded OPA authorization, and
a short-lived delegation token that binds the end user to the acting service, with no sidecar,
no proxy, and no central authorization server on the request path. The delegation layer is the
research contribution; the first three parts are the substrate it needs, and the benchmark
against Istio sidecar and Istio Ambient is the validation.
Objectives | O1: To design a Go middleware library that authenticates service-to-service calls using
SPIFFE/SPIRE workload identity and in-process mutual TLS, with no sidecar or proxy.
O2: To enforce fine-grained per-request authorization inside the service process using an
embedded Open Policy Agent engine, with no network call on the request path.
O3: To propagate end-user context across a multi-hop call chain using a short-lived delegation
token signed with the service's own SVID key and bound to the mutual TLS peer, closing the
confused deputy gap without a central authorization server.
O4: To build a demonstration multi-hop application and show the confused deputy attack
succeeding without the library and being blocked with it.
O5: To evaluate the library against a bare service, an Istio sidecar mesh and an Istio Ambient
mesh, measuring latency, memory and throughput, and reporting the cost of each security
property separately.
Any Other Details | Design documents (high level design, threat model, delegation token specification, evaluation
plan, API draft, ADRs, risk register, weekly meeting notes) are maintained in the project
Design folder. The high level design was baselined at v1.0 on 1 September 2026; changes after
that go through an architecture decision record.
Project hours per the Semester 7 timetable: Tuesday 11:35 to 13:15, Thursday 09:40 to 10:30,
Friday 14:05 to 16:35. Progress below is logged against those slots.
Phase I plan: design July to August 2026, implementation September to October 2026, first demo
October 2026, benchmark October to November 2026.

## Progress
Task Id | Task Name/Desc | Date of Review | Who | Completion Percent | Completion Status Desc (if needed) | Progress Report, Challenges, Work done | Review Comments
1 | Workload Identity |  |  | Completed |  | Identity layer for the library. A workload holds a SPIFFE SVID and a trust bundle, and everything else in the code reads them from one place.
1.1 | Repository set up and package layout | Tue 01 Sep 2026 | Dinesh V Masuti | 100 |  | New repository created for this phase, with the package split and the build and test commands working.
1.2 | Identity source interface |  | Praneesh R V | 100 |  | Agreed one interface for a workload identity so the rest of the code does not depend on where the certificate came from.
1.3 | In-process identity source | Thu 03 Sep 2026 | Dinesh V Masuti | 100 |  | Implementation of that interface for an identity held in memory. Lets the tests and the demo run on a laptop.
1.4 | SPIFFE ID reading and validation |  | Akash Varunn D | 100 |  | Reads the identity out of a certificate. Refuses anything ambiguous instead of picking one.
1.5 | SVID rotation handling | Fri 04 Sep 2026 | Sanjai K C K | 100 |  | Certificates are short lived, so the identity can be replaced while running. A replacement has to keep the same identity.
2 | SPIRE Integration |  |  | Ongoing |  | Getting identities from a SPIRE agent instead of generating them locally. Written, not yet run against a live server.
2.1 | Workload API client | Tue 08 Sep 2026 | Dinesh V Masuti | 60 | Pending live test | Connects to the SPIRE agent and follows the same interface as the in-process source. Still to be tested against a running SPIRE deployment.
2.2 | Start-up behaviour with no identity |  | Akash Varunn D | 100 |  | A service that cannot get an identity does not start serving.
3 | Mutual TLS Transport |  |  | Completed |  | Both ends of a call prove who they are, inside the service process. No sidecar or proxy involved.
3.1 | Server side configuration | Thu 10 Sep 2026 | Sanjai K C K | 100 |  | A caller without a valid certificate is turned away during the handshake, before any request handler runs.
3.2 | Client side configuration and peer checks |  | Sanjai K C K | 100 |  | The caller checks the service it reached. One correction here: the usual hostname check does not apply to these certificates and had to be replaced with an identity check.
3.3 | Peer identity available to handlers | Fri 11 Sep 2026 | Praneesh R V | 100 |  | Application code can read who called it, and gets nothing if the call did not come over a verified connection.
3.4 | Connection handling across rotation |  | Praneesh R V | 100 |  | Calls keep working when the certificate is replaced mid-run.
4 | Testing and Demonstration |  |  | Completed |  | Test coverage for the above, plus a small demo and the write-up for the review.
4.1 | Test certificate authority | Fri 11 Sep 2026 | Dinesh V Masuti | 100 |  | Issues certificates in process so the test suite needs no cluster. Test scaffolding only.
4.2 | Test suite | Sat 12 Sep 2026 | Akash Varunn D | 100 |  | Covers the normal path and the cases that should be refused: no certificate, wrong issuer, wrong service. Passes with the race detector on.
4.3 | Sample identity demo |  | Akash Varunn D | 100 |  | Prints the identities and certificates of two sample services, so what the code produces can be seen directly.
4.4 | Code and design documentation | Sun 14 Sep 2026 | Praneesh R V | 100 |  | Write-up of the code and the request flow, plus a rough design for the authorization and delegation parts that come next.